## Sheet1
What 3 Games Planning
Priority | Task | Sub-tasks | Hours
1 | Finish game engin | Dico APO | 2
1 | Hook game on map | event listener | 0.5
1 | Implement basic game 1: navigate map | can only move if correct answer mute listeners in meantime | 1
1 | Implement basic game 2: enter a journey | move trhu gmap steps | 3
1 | Play and stop buttons |  | 0.5
1 | LOGIN |  | 4
1 | Improve game w points | Build DB n models | 4
? |  | update DB at each points per user, journey, location | 3
? |  | Functions for ranking | 3
|  | Re-gam and skip buttons | 0.5
? | Views to see points and ranking per user (side menu), journey (side menu, see active, see all) location (infoWindow??) | Most likely Underscore templating | 5
| Styling | general layout | 12
|  | animation markers and moving through | 2
| Harcode bus route | w google Waypoints | 3
| Timeout function to go to next challenge | toggle on or off?? Always here?? | 2
| Creaet your own journey |  | 2
| Compete on s/o else's journey |  | 2
| Points system, | scrabble
quickness
became new best
Later | Location based refresh
|  | TOTAL TIME | 49.5